## Sheet1
Task Name | Duration | Start | Finish | Predecessors | Assigned to
**ONLINE INTERSHIP PORTAL | 64d | 2018-02-13 | 2018-05-11
*Requirements | 12d | 2018-02-13 | 2018-02-28
Problem Identification | 3d | 2018-02-13 | 2018-02-15 |  | All
lnterviev1s of Common People | 3d | 2018-02-16 | 2018-02-20 | 3 | Rahul,Rohan,Priyanka,Baibhav
Interviews of Company experts | 2d | 2018-02-21 | 2018-02-22 | 4 | Rahul,Rohan,Priyanka,Baibhav
Use Case Documentation | 4d | 2018-02-23 | 2018-02-28 | 5 | All
SRS Documentation | 4d | 2018-02-23 | 2018-02-28 | 5 | All
Conceptual Model | 2d | 2018-02-24 | 2018-03-25 | 7 | Rahul
Class Diagram | 2d | 2018-02-24 | 2018-03-25 | 7 | Rahul,Abhinav,Deboleena
UI Diagram | 2d | 2018-02-24 | 2018-03-25 | 10 | Rahul,Abhinav,Deboleena
Sequence Design | 6d | 2018-02-25 | 2018-02-26 | 5 | Abhinav,Deboleena
Creating the UI Design | 6d | 2018-02-25 | 2018-03-26 | 13 | Abhinav,Deboleena,Baibhav
Add Database | 6d | 2018-03-15 | 2018-03-17 | 13 | Abhinav,Deboleena,Baibhav
Login Page Coding | 3d | 2018-03-15 | 2018-03-17 | 15 | Abhinav
Forum Page Coding | 3d | 2018-03-15 | 2018-03-17 | 15 | Deboleena
Data Base Linking | 6d | 2018-03-23 | 2018-03-25 | 16 | Baibhav
Search Bar and logic Coding | 3d | 2018-03-28 | 2018-03-30 | 17 | Abhinav
Database viewing and logic coding | 3d | 2018-03-28 | 2018-03-30 | 17 | Deboleena
Company viewing Page coding | 3d | 2018-04-02 | 2018-04-04 | 21 | Baibhav
Unit Testing | 7d | 2018-04-10 | 2018-04-18 | 23 | Abhinav,Deboleena,Baibhav
Design Test Cases | 6d | 2018-03-23 | 2018-03-30 | 16 | Rohan
System Testing v0.1 | 5d | 2018-04-02 | 2018-04-06 | 26 | Rohan,Priyanka
Bug Fixing | 5d | 2018-04-09 | 2018-04-13 | 27 | Rahul,Rohan,Priyanka
Release0.1 | 3d | 2018-04-16 | 2018-04-18 | 28 | Rahul
System Testing v0.2 | 3d | 2018-04-19 | 2018-04-23 | 29 | Rohan,Priyanka
Release0.2 | 5d | 2018-04-24 | 2018-04-30 | 30 | Rahul
Extensive Testing | 5d | 2018-05-01 | 2018-05-07 | 31 | Rohan,Priyanka
Release 1.0 | 3d | 2018-05-08 | 2018-05-10 | 32 | Rahul
Final Project Demo | 1d | 2018-05-11 | 2018-05-11 | 33 | Rahul
CMMI Level2 Audit | 1d | 2018-05-11 | 2018-05-11 | 33 | Rahul